## Test Plan
Please Click Here to show my testplan full PDF.

## TestScenarios
Project Name | pickaboo.com
Reference Document
Created By | Safia Akther Chowdhury
Creation Date | 20-10-2024
Approval Date
Test Scenario ID | Features | Test Scenario Description | Priority | Number of Test Cases
TS_001 | Login | Validate the working of the "Login" functionality with valid and invalid credentials. | P0 | 20
TS_002 | Register Account | Validate the "Register Account" functionality, including form validations, error messages, and OTP verification. | P0 | 28
TS_003 | Logout | Validate the logout functionality to ensure the user session ends securely. | P0 | 15
TS_004 | Forgot Password | Validate the working of the "Forgot Password" feature for recovering user accounts. | P1 | 22
TS_005 | Purchase | Validate the purchase process, including adding products to the cart, applying discounts, and completing payment. | P1 | 25
TS_006 | Search | Validate the functionality of the search feature with valid and invalid inputs, including filtering and sorting. | P1 | 20
TS_007 | Product Listing | Validate the display of products with correct prices, images, and availability details on category and product pages. | P2 | 30
TS_008 | PC Builder | Validate the "PC Builder" functionality for customizing a PC configuration with all components and price updates. | P2 | 15
TS_009 | Wishlist | Validate the functionality of adding/removing products to/from the wishlist and checking availability from the wishlist. | P3 | 20
TS_010 | Notifications | Validate the display and functionality of notifications for order updates, promotional alerts, and system messages. | P3 | 12
TS_011 | Payment Options | Validate all payment options, including online payments, Cash on Delivery (COD), and EMI. | P0 | 25
TS_012 | Order Tracking | Validate the functionality of tracking orders, including status updates, shipping details, and delivery ETA. | P4 | 15
TS_013 | Account Management | Validate the management of user accounts, such as updating profiles, changing passwords, and viewing order history. | P4 | 20
TS_014 | Customer Support | Validate customer support options, such as live chat, raising tickets. | P5 | 15

## TestCase
Product Name |  | pickaboo | TC Start Date |  | TC Execution Start Date | - - |  |  |  |  | TEST CASE
Module Name |  | Account | TC End Date |  | TC Execution End Date | - - |  |  |  |  | PASS | 72
Epic |  |  | Test Case Developed By | Safia Akther Chowdhury | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | [5 empty] | NO RUN | 0
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 72
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Login |  | Email Login | Validate successful login with valid email and password | User logs in successfully and is redirected to the dashboard | As Expected | Email: valid@gmail.com Password: Valid123 | Enter valid email and password > Click Login button | N/A | N/A | Passed
2 | Login |  | Mobile Login | Validate successful login with valid mobile number and password | User logs in successfully and is redirected to the dashboard | As Expected | Mobile: 017XXXXXXXX Password: Valid123 | Enter valid mobile number and password > Click Login button | N/A | N/A | Passed
3 | Login |  | Invalid Email | Validate login attempt with invalid email | Error message: "Invalid email address" appears | As Expected | Email: invalid.com Password: Valid123 | Enter invalid email > Click Login button | N/A | N/A | Passed
4 | Login |  | Invalid Password | Validate login attempt with invalid password | Error message: "Incorrect password" appears | As Expected | Email: valid@gmail.com Password: Wrong123 | Enter valid email and invalid password > Click Login button | N/A | N/A | Passed
5 | Login |  | Blank Fields | Validate login attempt with both email/mobile and password fields blank | Error message: "Fields cannot be empty" appears | As Expected | None | Leave email and password blank > Click Login button | N/A | N/A | Passed
6 | Login |  | OTP Login | Validate the visibility and functionality of OTP login option | OTP login option is visible and sends OTP on entering a valid number | As Expected | Mobile: 017XXXXXXXX | Select OTP login > Enter valid mobile number > Click Send | N/A | N/A | Passed
7 | Login |  | Password Masking | Validate that the password field is masked during entry | Password characters are masked | As Expected | Password: Valid123 | Enter password and check masking behavior | N/A | N/A | Passed
8 | Login |  | Password Toggle | Validate the functionality of the "eye" icon to toggle password visibility | Password is displayed when "eye" icon is clicked | As Expected | Password: Valid123 | Click the "eye" icon > Check password visibility | N/A | N/A | Passed
9 | Login |  | SQL Injection | Validate the login form against SQL injection attacks | Login form blocks SQL commands and displays an error message | As Expected | Email: ' OR 1=1 -- | Enter malicious SQL code in email > Click Login | N/A | N/A | Passed
10 | Login |  | Error Messaging | Validate the clarity and accuracy of error messages | Error messages are user-friendly and relevant | As Expected | Email: invalid@gmail.com | Enter invalid email > Check error message | N/A | N/A | Passed
11 | Login |  | Google Login | Validate login via Google | User is successfully authenticated and redirected to the dashboard | As Expected | Google account | Click Google login > Enter valid credentials | N/A | N/A | Passed
12 | Login |  | Facebook Login | Validate login via Facebook | User is successfully authenticated and redirected to the dashboard | As Expected | Facebook account | Click Facebook login > Enter valid credentials | N/A | N/A | Passed
13 | Login |  | Forgotten Password | Validate the functionality of the "Forgot your password?" link | Password recovery page is displayed | As Expected | Email: valid@gmail.com | Click Forgot your password? > Enter email > Click Submit | N/A | N/A | Passed
14 | Login |  | Expired Session | Validate login attempt after session expiry | User is redirected to login page with a relevant message | As Expected | None | Let the session expire > Try accessing a secured page | N/A | N/A | Passed
15 | Login |  | Brute Force Attack | Validate the account lockout mechanism after multiple failed login attempts | Account is locked after 5 failed attempts and displays an appropriate message | As Expected | Invalid Password (5 times) | Enter wrong password 5 times > Check account lock message | N/A | N/A | Passed
16 | Login |  | Invalid OTP | Validate login with invalid OTP | Error message: "Invalid OTP" appears | As Expected | OTP: 123456 | Enter invalid OTP > Click Continue | N/A | N/A | Passed
17 | Login |  | Slow Network | Validate login behavior under slow network conditions | Login succeeds after a slight delay or shows appropriate error message | As Expected | Valid Email/Password | Simulate slow network > Try logging in | N/A | N/A | Passed
18 | Login |  | Logout Redirect | Validate redirection to the login page after a successful logout | User is redirected to the login page | As Expected | Valid Login | Login > Logout > Check redirection | N/A | N/A | Passed
19 | Login |  | Mobile UI | Validate login form UI and responsiveness on mobile devices | Login form adjusts properly to mobile screen size | As Expected | Mobile Device | Open login form on mobile > Check responsiveness | N/A | N/A | Passed
20 | Login |  | Strong Passwords | Validate that the system recommends strong password usage | Strong password recommendation message appears | As Expected | Password: Weak123 | Try setting a weak password > Check for recommendation | N/A | N/A | Passed
Passed
1 | Register Account |  | Form Validation | Verify the user can register with valid First Name, Last Name, valid Mobile Number, and correct OTP. | Registration should be successful, and the user should be redirected to the dashboard. | As Expected | Name: John Doe, Mobile: 0123456789 | 1. Open the Pickaboo registration form. 2. Enter valid inputs. 3. Submit the form. | N/A | N/A | Passed
2 | Register Account |  | Input Validation | Verify the error message when leaving the First Name field empty. | Error: "First Name is required." | As Expected | N/A | 1. Open the registration form. 2. Leave the First Name field blank. 3. Submit the form. | N/A | N/A | Passed
3 | Register Account |  | Input Validation | Verify the error message when entering numbers in the First Name field. | Error: "Invalid input for First Name." | As Expected | First Name: 12345 | 1. Open the registration form. 2. Enter numbers in the First Name field. 3. Submit the form. | N/A | N/A | Passed
4 | Register Account |  | Input Validation | Verify the error message when the Mobile Number field is left blank. | Error: "Mobile Number is required." | As Expected | N/A | 1. Open the registration form. 2. Leave the Mobile Number field blank. 3. Submit the form. | N/A | N/A | Passed
5 | Register Account |  | OTP Process | Verify the Send OTP button generates a valid OTP for a registered mobile number. | OTP should be generated and sent to the mobile number. | As Expected | Mobile: 0123456789 | 1. Open the registration form. 2. Enter a valid mobile number. 3. Click Send OTP. | N/A | N/A | Passed
6 | Register Account |  | OTP Validation | Verify the error message when entering an invalid OTP. | Error: "Invalid OTP. Please try again." | As Expected | OTP: 0000 | 1. Open the registration form. 2. Enter a valid mobile number. 3. Enter an invalid OTP. 4. Click Continue. | N/A | N/A | Passed
7 | Register Account |  | Mobile Number Format | Verify the error message for entering a mobile number without the country code or with fewer digits. | Error: "Invalid Mobile Number." | As Expected | Mobile: 12345 | 1. Open the registration form. 2. Enter an incomplete mobile number. 3. Click Send OTP. | N/A | N/A | Passed
8 | Register Account |  | T&C Agreement | Verify the user cannot proceed if the Terms & Conditions checkbox is not selected. | Error: "You must accept the Terms and Conditions to register." | As Expected | N/A | 1. Open the registration form. 2. Fill all fields correctly. 3. Leave the T&C checkbox unchecked. 4. Submit the form. | N/A | N/A | Passed
9 | Register Account |  | Captcha Verification | Verify if a Captcha is implemented to prevent bots from registering. | Captcha should appear before the registration is submitted. | As Expected |  | 1. Complete the registration form. 2. Check for Captcha presence before submission. | N/A | N/A | Passed
10 | Register Account |  | Social Media Signup | Verify the user can register via Google integration. | Registration via Google should log the user into their account. | As Expected | Google Test Account | 1. Open the registration form. 2. Click the Google registration button. 3. Use valid credentials. | N/A | N/A | Passed
11 | Register Account |  | Mobile Number Validation | Verify error message when entering an already registered mobile number. | Error: "This mobile number is already registered." | As Expected | Mobile: 0123456789 | 1. Open the registration form. 2. Enter a mobile number that is already registered. 3. Submit the form. | N/A | N/A | Passed
12 | Register Account |  | Button Functionality | Verify the Send OTP button becomes disabled after clicking once. | Send OTP button should be disabled temporarily to prevent multiple clicks. | As Expected | Mobile: 0123456789 | 1. Open the registration form. 2. Enter a valid mobile number. 3. Click Send OTP multiple times. | N/A | N/A | Passed
13 | Register Account |  | Field Validation | Verify error message when entering special characters in the Last Name field. | Error: "Invalid characters in Last Name." | As Expected | Last Name: @#*! | 1. Open the registration form. 2. Enter special characters in the Last Name field. 3. Submit the form. | N/A | N/A | Passed
14 | Register Account |  | OTP Expiry | Verify error message when entering an expired OTP. | Error: "OTP has expired. Please request a new OTP." | As Expected | OTP: 1234 | 1. Open the registration form. 2. Request OTP. 3. Wait for OTP to expire. 4. Enter expired OTP and click Continue. | N/A | N/A | Passed
15 | Register Account |  | Input Length | Verify the system does not accept a mobile number exceeding the valid length (e.g., 11 digits). | Error: "Mobile number is too long." | As Expected | Mobile: 01234567891234 | 1. Open the registration form. 2. Enter a mobile number longer than 11 digits. 3. Submit the form. | N/A | N/A | Passed
16 | Register Account |  | Input Length | Verify the system does not accept a mobile number shorter than the valid length (e.g., less than 11 digits). | Error: "Invalid Mobile Number." | As Expected | Mobile: 01234 | 1. Open the registration form. 2. Enter a mobile number shorter than 11 digits. 3. Submit the form. | N/A | N/A | Passed
17 | Register Account |  | Input Validation | Verify error message when entering numbers in the Last Name field. | Error: "Invalid characters in Last Name." | As Expected | Last Name: 1234 | 1. Open the registration form. 2. Enter numbers in the Last Name field. 3. Submit the form. | N/A | N/A | Passed
18 | Register Account |  | UI Feedback | Verify the Continue button remains disabled until all required fields are filled. | The Continue button should remain disabled until all fields are filled. | As Expected | N/A | 1. Open the registration form. 2. Leave some fields blank. 3. Check the status of the Continue button. | N/A | N/A | Passed
19 | Register Account |  | Cross-Browser Testing | Verify registration functionality across supported browsers (e.g., Chrome, Firefox, Edge). | Registration should work correctly on all supported browsers. | As Expected | N/A | 1. Open the registration form on different browsers. 2. Complete the registration process. 3. Verify results. | N/A | N/A | Passed
20 | Register Account |  | SQL Injection | Verify that SQL injection attempts (e.g., ' OR 1=1 --) are prevented during the registration process. | System should prevent registration and display an error message. | As Expected | Test Input: ' OR 1=1 -- | 1. Open the registration form. 2. Enter SQL injection attempts in input fields. 3. Submit the form. | N/A | N/A | Passed
21 | Register Account |  | Accessibility | Verify the registration form is accessible to screen readers and follows accessibility guidelines (e.g., labels for all input fields). | The form should be readable by screen readers, and all fields should have descriptive labels. | As Expected | N/A | 1. Open the registration form. 2. Enable a screen reader. 3. Verify accessibility compliance. | N/A | N/A | Passed
22 | Register Account |  | Mobile Responsiveness | Verify the registration form is responsive and works properly on mobile devices. | The form should adjust to the mobile screen size, and all buttons/fields should be usable. | As Expected | N/A | 1. Open the registration form on a mobile device. 2. Complete the registration process. 3. Verify functionality and UI. | N/A | N/A | Passed
23 | Register Account |  | Field Validation | Verify the First Name field accepts alphabets and spaces but no special characters. | Field should accept valid input only. | As Expected | First Name: John Smith | 1. Open the registration form. 2. Enter alphabets and spaces in the First Name field. 3. Submit the form. | N/A | N/A | Passed
24 | Register Account |  | Confirmation Message | Verify a confirmation message appears upon successful registration. | Message: "Registration successful. Welcome to Pickaboo!" | As Expected | N/A | 1. Open the registration form. 2. Fill all fields correctly. 3. Submit the form. 4. Verify the confirmation message. | N/A | N/A | Passed
25 | Register Account |  | Data Privacy | Verify that passwords are not stored or displayed in plain text during the registration process. | Passwords should be hashed/encrypted and not visible. | As Expected | N/A | 1. Open the registration form. 2. Fill the fields. 3. Check network calls for password data. | N/A | N/A | Passed
26 | Register Account |  | Social Media Login | Verify the Google Login option allows registration using a valid Google account. | User should be able to log in and register successfully with their Google account. | As Expected | Google Account: user@gmail.com | 1. Open the registration form. 2. Click on the Google button. 3. Select a valid Google account. 4. Complete the login process. | N/A | N/A | Passed
27 | Register Account |  | Social Media Login | Verify the Facebook Login option allows registration using a valid Facebook account. | User should be able to log in and register successfully with their Facebook account. | As Expected | Facebook Account: user123 | 1. Open the registration form. 2. Click on the Facebook button. 3. Enter valid Facebook credentials. 4. Complete the login process. | N/A | N/A | Passed
28 | Register Account |  | Mandatory Fields | Verify error messages appear for all mandatory fields if left blank and submitted. | Error messages should appear for all empty mandatory fields: First Name, Last Name, Mobile Number, and OTP. | As Expected | N/A | 1. Open the registration form. 2. Leave all mandatory fields blank. 3. Click the Continue button. 4. Verify the error messages for each field. | N/A | N/A | Passed
Passed
Passed
Passed
1 | Logout |  | Logout Functionality | Verify that the user is successfully logged out when clicking the "Log Out" option. | User is redirected to the login page, and the session is terminated. | As Expected | N/A | 1. Login to Pickaboo. 2. Click on "My Account". 3. Click "Log Out". | N/A | N/A | Passed
2 | Logout |  | Session Termination | Verify that after logout, accessing a previously opened page redirects the user to the login page. | User cannot access secured pages and is redirected to the login page. | As Expected | N/A | 1. Login to Pickaboo. 2. Open a secured page (e.g., Wishlist). 3. Click "Log Out". 4. Try accessing the secured page again. | N/A | N/A | Passed
3 | Logout |  | Button Placement | Verify that the "Log Out" option is easily visible under the "My Account" dropdown. | "Log Out" is clearly visible without the need to scroll. | As Expected | N/A | 1. Login to Pickaboo. 2. Click on "My Account". 3. Observe the visibility of "Log Out" option. | N/A | N/A | Passed
4 | Logout |  | Confirmation Message | Verify if a confirmation prompt appears when the user clicks "Log Out". | No confirmation prompt should appear; the user should be logged out immediately. | As Expected | N/A | 1. Login to Pickaboo. 2. Click on "My Account". 3. Click "Log Out". | N/A | N/A | Passed
5 | Logout |  | Auto Logout | Verify that clicking "Log Out" automatically ends the session without manual refresh. | The user session ends immediately, and the user is redirected to the login page without needing to refresh manually. | As Expected | N/A | 1. Login to Pickaboo. 2. Click on "My Account". 3. Click "Log Out". | N/A | N/A | Passed
6 | Logout |  | Invalid Session | Verify that clicking "Log Out" with an invalid session does not cause errors. | User is redirected to the login page without any errors. | As Expected | N/A | 1. Login to Pickaboo. 2. Tamper with session cookies or tokens. 3. Click "Log Out". | N/A | N/A | Passed
7 | Logout |  | Session Token | Verify that the session token is destroyed after logging out. | Session tokens/cookies are invalidated and deleted upon logout. | As Expected | N/A | 1. Login to Pickaboo. 2. Click "Log Out". 3. Inspect browser cookies/tokens to ensure they are invalidated. | N/A | N/A | Passed
8 | Logout |  | Redirect Page | Verify that the user is redirected to the login page after clicking "Log Out". | User is redirected to the login page immediately after logging out. | As Expected | N/A | 1. Login to Pickaboo. 2. Click "Log Out". 3. Observe redirection to the login page. | N/A | N/A | Passed
9 | Logout |  | Multiple Tabs Logout | Verify that logging out in one browser tab logs out the user from all other active tabs. | All active tabs redirect to the login page after logout. | As Expected | Multiple logged-in sessions | 1. Login to Pickaboo on multiple browser tabs. 2. Click "Log Out" in one tab. 3. Check other tabs for logout status. | N/A | N/A | Passed
10 | Logout |  | Mobile Logout | Verify logout functionality on mobile devices. | Logout works properly and redirects the user to the login page on mobile devices. | As Expected | Mobile Device | 1. Login to Pickaboo on a mobile device. 2. Click "Log Out". 3. Observe redirection to the login page. | N/A | N/A | Passed
11 | Logout |  | Logout Without Login | Verify that clicking "Log Out" without being logged in does not cause errors. | No errors occur, and the user remains on the login page or sees an appropriate message. | As Expected | Not logged-in | 1. Open Pickaboo login page. 2. Attempt to click "Log Out" (if accessible via URL). | N/A | N/A | Passed
12 | Logout |  | Logout Response Time | Verify that the logout process completes within 2 seconds. | Logout redirects the user to the login page within 2 seconds. | As Expected | N/A | 1. Login to Pickaboo. 2. Click "Log Out". 3. Measure the time taken to redirect to the login page. | N/A | N/A | Passed
13 | Logout |  | Logout Button Color | Verify that the "Log Out" option has a distinct color to differentiate it from other options. | "Log Out" option is visually distinguishable (e.g., different color) from other dropdown items. | As Expected | N/A | 1. Login to Pickaboo. 2. Open "My Account" dropdown. 3. Observe the color of "Log Out" option. | N/A | N/A | Passed
14 | Logout |  | Cross-Browser Logout | Verify that logging out in one browser ends the session in all other browsers. | Logging out in one browser invalidates the session in all other browsers, redirecting them to the login page. | As Expected | Multiple browser sessions | 1. Login to Pickaboo on Browser A and Browser B. 2. Click "Log Out" on Browser A. 3. Check Browser B for logout status. | N/A | N/A | Passed
15 | Logout |  | Post-Purchase Logout | Verify logout functionality immediately after completing a purchase. | User is successfully logged out and redirected to the login page after logout post-purchase. | As Expected | Completed Purchase | 1. Login to Pickaboo. 2. Complete a purchase. 3. Click "Log Out". 4. Observe redirection to the login page. | N/A | N/A | Passed
1 | Forgot Password |  | Forgot Password Page Loading | Verify that the Forgot Password page loads successfully. | Forgot Password page should load with the input field and "Continue" button. | Forgot Password page loaded successfully. | N/A | Click on "Forgot Password" from login screen. | N/A | N/A | Passed
2 | Forgot Password |  | Input Field Placeholder | Verify that the placeholder text for the input field appears as expected. | Placeholder text should be "Mobile Number/Email." | Placeholder text is displayed correctly. | N/A | Open Forgot Password page and check the input field. | N/A | N/A | Passed
3 | Forgot Password |  | Empty Field Validation | Verify clicking "Continue" without input data shows an error message. | Error message: "Please fill out this field." | Error message appears as expected. | N/A | Leave the input field blank and click "Continue." | N/A | N/A | Passed
4 | Forgot Password |  | Valid Input | Verify that entering a valid registered email/mobile allows password reset. | Confirmation message appears. | Confirmation message appears as expected. | Valid email: user@site.com | Enter registered email/mobile and click "Continue." | N/A | N/A | Passed
5 | Forgot Password |  | Invalid Email Format | Verify error message for invalid email format. | Error message: "Enter a valid email address." | Error message appears as expected. | Invalid email: invalid | Enter invalid email format and click "Continue." | N/A | N/A | Passed
6 | Forgot Password |  | Unregistered Email/Mobile | Verify error message for unregistered email/mobile. | Error message: "Email/Mobile not registered." | Error message appears as expected. | Unregistered mobile: 12345 | Enter unregistered mobile and click "Continue." | N/A | N/A | Passed
7 | Forgot Password |  | Resending Reset Link | Verify that the user can resend the reset link to the same email. | Reset link resent message appears. | Reset link message appears as expected. | Registered email: user@site.com | Click "Resend Link" option after entering registered email. | N/A | N/A | Passed
8 | Forgot Password |  | Button Alignment | Verify that the "Continue" button is properly aligned on the page. | Button should be aligned centrally below the input field. | Button is aligned as expected. | N/A | Inspect button alignment on Forgot Password page. | N/A | N/A | Passed
9 | Forgot Password |  | Case Sensitivity in Email | Verify if email input is case-sensitive. | System should accept both uppercase and lowercase emails. | Case-insensitive functionality works. | Valid email: User@SITE.com | Enter uppercase email and click "Continue." | N/A | N/A | Passed
10 | Forgot Password |  | Error Message Text | Verify error message text clarity. | Error message text should be clear and concise. | Error message is clear as expected. | N/A | Trigger validation errors intentionally. | N/A | N/A | Passed
11 | Forgot Password |  | Multiple Reset Attempts | Verify limiting reset attempts to avoid misuse. | System should display a warning after 3 invalid attempts. | Warning displayed after multiple invalid attempts. | Invalid data: random | Enter invalid data repeatedly and observe system behavior. | N/A | N/A | Passed
12 | Forgot Password |  | Verify Error Timeout | Ensure error message disappears after a timeout. | Error message should disappear after 5 seconds. | Error message disappears as expected. | N/A | Trigger validation errors and wait for 5 seconds. | N/A | N/A | Passed
13 | Forgot Password |  | Response Time | Verify that the system responds promptly after "Continue" is clicked. | Response time should be within 2 seconds. | System responds within expected time. | N/A | Click "Continue" and measure response time. | N/A | N/A | Passed
14 | Forgot Password |  | Mobile Responsiveness | Verify Forgot Password page behavior on mobile devices. | Page layout and functionality should work on mobile. | Mobile view works as expected. | N/A | Test the page on a mobile browser. | N/A | N/A | Passed
15 | Forgot Password |  | Special Characters in Input | Verify input validation for special characters. | System should reject input with special characters. | System rejects invalid inputs as expected. | Invalid data: @#*& | Enter special characters and click "Continue." | N/A | N/A | Passed
16 | Forgot Password |  | Input Field Masking | Verify input field masking for sensitive data. | Input should not be masked (visible). | Input field is not masked as expected. | N/A | Enter data and observe input field behavior. | N/A | N/A | Passed
17 | Forgot Password |  | Page Alignment | Verify overall page alignment and element spacing. | Page should appear aligned and professional. | Page alignment is correct. | N/A | Check alignment of text, buttons, and input fields. | N/A | N/A | Passed
18 | Forgot Password |  | Valid Mobile Number Reset | Verify password reset functionality using a valid mobile number. | Confirmation message appears. | Confirmation message appears as expected. | Valid mobile: 017XXXXXXXX | Enter valid mobile number and click "Continue." | N/A | N/A | Passed
19 | Forgot Password |  | Empty Field Error Focus | Ensure error highlights the correct field when empty. | Input field should be highlighted in red. | Input field is highlighted as expected. | N/A | Leave input blank and click "Continue." | N/A | N/A | Passed
20 | Forgot Password |  | Email Linking with Accounts | Verify the system only allows email/mobile linked to existing accounts. | Unlinked emails should display error: "Not Registered." | Error appears as expected for unlinked data. | Unregistered email/mobile | Enter unregistered data and click "Continue." | N/A | N/A | Passed
21 | Forgot Password |  | Input Data Truncation | Ensure long input data is truncated to prevent system overload. | Input data should be truncated beyond limit. | Input truncation works as expected. | Input > 1000 characters | Enter excessively long input data. | N/A | N/A | Passed
22 | Forgot Password |  | Confirmation Message Display | Verify confirmation message clarity and position on the page. | Message should appear above input field in readable font. | Confirmation message is displayed correctly. | Registered email/mobile | Complete the reset process and observe message. | N/A | N/A | Passed
1 | Search |  | Search bar usability | Verify the visibility of the search bar | The search bar should be visible on the homepage | The search bar is visible on the homepage | N/A | Navigate to the Pickaboo homepage and locate the search bar | N/A | N/A | Passed
2 | Search |  | Search functionality | Enter a valid product name in the search bar and click the search icon | Relevant products should appear in the results | Relevant products appear in the results | "Smartphone" | Enter "Smartphone" in the search bar and click the search icon | N/A | N/A | Passed
3 | Search |  | No results | Enter an invalid product name in the search bar | "No results found" message should be displayed | "No results found" message is displayed | "xyzabc123" | Enter "xyzabc123" in the search bar and press the search icon | N/A | N/A | Passed
4 | Search |  | Placeholder text | Verify the placeholder text inside the search bar | Placeholder text should be "Search for products, brands and more" | Placeholder text is "Search for products, brands and more" | N/A | Navigate to the homepage and check the placeholder text of the search bar | N/A | N/A | Passed
5 | Search |  | Case sensitivity | Enter a valid product name in lowercase letters | Search results should not be case-sensitive | Search results are not case-sensitive | "headphone" | Enter "headphone" in lowercase and verify results | N/A | N/A | Passed
6 | Search |  | Case sensitivity | Enter a valid product name in uppercase letters | Search results should not be case-sensitive | Search results are not case-sensitive | "HEADPHONE" | Enter "HEADPHONE" in uppercase and verify results | N/A | N/A | Passed
7 | Search |  | Partial search terms | Enter a partial product name | Results should match the partial search term | Results match the partial search term | "phone" | Enter "phone" and check the results | N/A | N/A | Passed
8 | Search |  | Search with numbers | Enter a product name that contains numbers | Results should include products with the specified name and numbers | Results include products with the specified name and numbers | "iPhone 13" | Enter "iPhone 13" and check the results | N/A | N/A | Passed
9 | Search |  | Suggestions feature | Verify if suggestions are displayed when typing a keyword | Relevant product suggestions should appear | Relevant suggestions appear | "headp" | Type "headp" and observe suggestions | N/A | N/A | Passed
10 | Search |  | Redirect after search | Perform a search and click on a product | User should be redirected to the product details page | User is redirected to the product details page | "Laptop" | Search "Laptop" and click a product | N/A | N/A | Passed
11 | Search |  | Response time | Perform a search and measure the time taken to display results | Search results should be displayed within 2 seconds | Search results are displayed within 2 seconds | "TV" | Search "TV" and measure the response time | N/A | N/A | Passed
12 | Search |  | Clear input field | Enter text in the search bar and clear it manually | The input field should be cleared | The input field is cleared | N/A | Enter text in the search bar, press the "x" button or delete the text | N/A | N/A | Passed
13 | Search |  | Search icon visibility | Verify the visibility of the search icon | The search icon should be visible | The search icon is visible | N/A | Navigate to the homepage and locate the search icon | N/A | N/A | Passed
14 | Search |  | Enter key functionality | Perform a search by pressing the "Enter" key instead of the search icon | Search should work upon pressing "Enter" | Search works upon pressing "Enter" | "Camera" | Enter "Camera" and press "Enter" | N/A | N/A | Passed
15 | Search |  | Long product name | Enter a long product name and search | Relevant results should be displayed | Relevant results are displayed | "Wireless headphones with mic" | Enter "Wireless headphones with mic" and search | N/A | N/A | Passed
16 | Search |  | Back button navigation | Perform a search and navigate back using the browser's back button | User should return to the homepage or previous search | User returns to the previous page or homepage | "Shoes" | Search "Shoes" and click the back button | N/A | N/A | Passed
17 | Search |  | Multiple searches | Perform multiple searches one after another | Each search should display relevant results | Each search displays relevant results | Multiple search terms | Search "Watch," "Tablet," "Speaker" consecutively | N/A | N/A | Passed
18 | Search |  | SQL injection attempt | Enter SQL injection script in the search bar | Application should not crash or return unexpected data | Application does not crash or return unexpected data | "' OR 1=1 --" | Enter "' OR 1=1 --" in the search bar and check the response | N/A | N/A | Passed
19 | Search |  | Search button alignment | Verify the alignment of the search button | The search button should be aligned properly | The search button is aligned properly | N/A | Inspect the alignment of the search button visually | N/A | N/A | Passed
20 | Search |  | Browser compatibility | Perform a search on different browsers (Chrome, Firefox, Safari) | Search functionality should work correctly across all tested browsers | Search functionality works correctly across all tested browsers | "Smartwatch" | Perform a search for "Smartwatch" on multiple browsers | N/A | N/A | Passed
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [6 empty] | Result :
Project Name | Pickaboo
Module Name | Account,logout,forgot password,search |  |  |  |  | Total No. | Status
Feature Name
Test Case Version | [5 empty] | 72 | PASS
Written By | [5 empty] | 0 | FAIL
Executed By | [5 empty] | 0 | Not Executed | New Features:- | Testing Scope:- | Testing Environment :Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 72 | 0 | 0 | 0 | 72
Grand Total | 72 | 0 | 0 | 0 | 72
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (105/105)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/105)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (72/105)*100 = 68.57%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (0/105)*100 = 0%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/105)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Bug Report (hidden)
Bug Reporting
# SL 01
Issue: Registered with invalid email address.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the files with valid credentials. 4. Click 'Continue'.
Env: Production.
Module: Register
Priority: High ¦ Medium ¦ Low
Severity: Blocker ¦ Critical ¦ Major ¦ Minor
Screenshot: Invalid email address error
Expected: Should not allow registration with invalid email address.
Responsible QA: Tashfiquzzman
Bug Reporting
# SL 02
Issue: Click on "Forgotten Password?" and Account deleted
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P2
Screenshot: "Forgotten Password" error
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 03
Issue: First and last names should not start with a special character.
Reproducing Steps:
1. Goto the URL https:/www.startech.com.bd 2. Click on the Register button at the right corner. 3. Fill all the fiels with valid credentials
4. Click 'Continue'.
Env: Production.
Module: Register
Severity: P4
Screenshot: First and last names should not start with a special characte
Responsible QA: Tashfiquzzman
Bug Reporting
# SL 04
issue:First name and last name should not start with number.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P5
Screenshot: First name error
Responsible QA: Tashfiquzzaman
Bug Reporting
# SL 05
issue: A comma should not be expected between the name field.
Reproducing Steps:
1. Goto the URL https://www.startech.com.bd 2. Click on the Login button at the right corner 3. Fill all the fields with invalid credentials 4. Click ''Forgotten Password?"
Env: Production
Module: Login
Severity: P6
Screenshot: Comma error in first name.
Responsible QA: Tashfiquzzaman